## Sheet1
List Develop and Support Tahun 2021 - 2022 |  |  |  | Done
On Progress
Queue
No | Project and Support | Detail | Status | Approval MTI | Head PIC | PIC | Start | End | Plan Date
1 | Sales Monitoring Report | Update master target sales import dan export periode 2022 | Done | Approve | AR | MH | 25 Dec 2021 08.00 | 25 Dec 2021 09.00 | 2021-12-25
|  | Create script & query function detail target import 2022 | Done |  |  | MH | 25 Dec 2021 09.00 | 25 Dec 2021 10.00
|  | Create script & query function detail target export 2022 | Done |  |  | MH | 25 Dec 2021 10.00 | 25 Dec 2021 12.00
2 | Dwelling time terminal | Update script periode 2022 | Done | Approve | AR | MH | 25 Dec 2021 13.00 | 25 Dec 2021 14.00 | 2021-12-25
|  | Update store procedure 2022 | Done |  |  | MH | 25 Dec 2021 14.00 | 25 Dec 2021 15.00
3 | Dwelling time non terminal | Update script periode 2022 | Done | Approve | AR | MH | 25 Dec 2021 15.00 | 25 Dec 2021 16.00 | 2021-12-25
|  | Update store procedure 2022 | Done |  |  | MH | 25 Dec 2021 16.00 | 25 Dec 2021 17.00
4 | Dwelling time emplacement | Update script periode 2022 | Done | Approve | AR | AR | 25 Dec 2021 08.00 | 25 Dec 2021 10.00 | 2021-12-25
|  | Update store procedure 2022 | Done |  |  | AR | 25 Dec 2021 10.00 | 25 Dec 2021 12.00
5 | Inventory Report Container (Customer/Shippingline) | Update Data Periode 2022 | Done | Approve | AR | AR | 25 Dec 2021 13.00 | 25 Dec 2021 15.00 | 2021-12-25
6 | Master Tarif Shipping Line | Update master tarif periode 2022 | Done | Approve | AR | AR | 25 Dec 2021 15.00 | 25 Dec 2021 16.00 | 2021-12-25
|  | Update store procedure master tarif | Done |  |  | AR | 25 Dec 2021 16.00 | 25 Dec 2021 17.00
7 | Master Tarif Terminal | Update master tarif periode 2022 | Done | Approve | AR | MH | 26 Dec 2021 08.00 | 26 Dec 2021 10.00 | 2021-12-26
|  | Update store procedure master tarif | Done |  |  | MH | 26 Dec 2021 10.00 | 26 Dec 2021 12.00
8 | Master Tarif Feeder | Update master tarif periode 2022 | Done | Approve | AR | MH | 26 Dec 2021 13.00 | 26 Dec 2021 14.00 | 2021-12-26
|  | Update store procedure master tarif | Done |  |  | MH | 26 Dec 2021 14.00 | 26 Dec 2021 15.00
9 | Master Tarif PLB | Update master tarif periode 2022 | Done | Approve | AR | MH | 26 Dec 2021 15.00 | 26 Dec 2021 16.00 | 2021-12-26
|  | Update store procedure master tarif | Done |  |  | MH | 26 Dec 2021 16.00 | 26 Dec 2021 17.00
10 | Master Tarif Non Terminal | Update master tarif periode 2022 | Done | Approve | AR | AR | 26 Dec 2021 08.00 | 26 Dec 2021 11.00 | 2021-12-26
|  | Update store procedure master tarif | Done |  |  | AR | 26 Dec 2021 11.00 | 26 Dec 2021 12.00
11 | Master Customer Discount tarif | Update master tarif periode 2022 | Done | Approve | AR | AR | 26 Dec 2021 13.00 | 26 Dec 2021 15.00 | 2021-12-26
|  | Update store procedure master tarif | Done |  |  | AR | 26 Dec 2021 15.00 | 26 Dec 2021 17.00
12 | Cutoff Tax Invoice Periode 2021 | Update cutoff master tax periode 2021 | On Progress | Approve | AR | AR |  |  | 2021-12-31
|  | Update store procedure tax invoice | On Progress |  |  | MH
13 | Monitoring All report & Invoive Periode 2022 | Monitoring Report, SO dan invoice terminal | On Progress | Approve | AR | MH |  |  | 2022-01-01
|  | Monitoring Report, SO dan invoice non terminal | On Progress |  |  | AR
|  | Monitoring Report, SO dan invoice feeder | On Progress |  |  | MH
|  | Monitoring Report, SO dan invoice PLB | On Progress |  |  | AR
14 | Re-Develop Autogate | Analisa Flow Proses System Di Lapangan | Queue | - | MH |  |  |  | Jan 2022 - Jul 2022
|  | - Analisa Sistem OCR SecurOS | Queue
|  | - Analisa Sistem Controller EntryPass | Queue
|  | - Analisa Sistem Platform 1 (EntryPass) | Queue
|  | - Analisa Data Reader Tapping CID Card | Queue
|  | - Analisa Sistem PembARan Data P1 melalui Log Data Reader dan OCR | Queue
|  | - Analisa PembARan Data melalui Websocket | Queue
|  | Develop Background Service Apps | Queue
|  | - Develop Reader tapping CID Card | Queue
|  | - Develop reader data OCR | Queue
|  | - Develop Logic Data CID dan OCR | Queue
|  | - Develop Realtime process receive and sending data XML | Queue
|  | - Develop Sending Data to Log P1 File (P1Imp_) | Queue
|  | - Develop Reader API Background Service | Queue
|  | - Develop Sending Data to Database | Queue
|  | Develop Database Autogate | Queue
|  | - Develop tabel concept and indexing tabel | Queue
|  | - Develop view dan store procedure database | Queue
|  | Develop API Server | Queue
|  | - Develop structure model API | Queue
|  | - Develop JSON Data Concept | Queue
|  | Develop iKios System | Queue
|  | - Develop Receipt Data from Background System | Queue
|  | - Develop Dashboard iKios System | Queue
|  | Develop Front-End Autogate System | Queue
|  | - Develop Modul Gate Monitoring | Queue
|  | - Develop Modul Manual Gate Process (CSV Manual) | Queue
|  | - Develop Modul Realtime Reader Data from Database | Queue
|  | - Develop Modul Dashboard Autogate | Queue
|  | - Develop Modul Report Autogate | Queue
|  | Testing & UAT System Autogate | Queue
|  | Re-Testing & Bug Fix | Queue
|  | Go-Live | Queue
15 | Scan QRCODE Fitur MyCDP | Design Flow Concept | Queue | - | MH |  |  |  | Jan 2022 - Dec 2022
|  | Design Tabel and Procedure Database | Queue
|  | Develop fitur with vendor | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Live | Queue
16 | Develop Export Modul MyCDP | Design Flow Concept | Queue | - | MH |  |  |  | Jan 2022 - Dec 2022
|  | Design Tabel and Procedure Database | Queue
|  | Develop fitur with vendor | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Live | Queue
17 | Upload Document Feeder Fitur MyCDP | Design Flow Concept | Queue | - | MH |  |  |  | Jan 2022 - Dec 2022
|  | Design Tabel and Procedure Database | Queue
|  | Develop fitur with vendor | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Live | Queue
18 | Download EIR Fitur MyCDP | Design Flow Concept | Queue | - | MH |  |  |  | Jan 2022 - Dec 2022
|  | Design Tabel and Procedure Database | Queue
|  | Develop fitur with vendor | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Live | Queue
19 | Payment Manual Transaction Fitur MyCDP | Design Flow Concept | Queue | - | MH |  |  |  | Jan 2022 - Dec 2022
|  | Design Tabel and Procedure Database | Queue
|  | Develop fitur with vendor | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Live | Queue
20 | Develop module Behandle DoSS | Design Flow Concept | Queue | - | MH |  |  |  | Jan 2022 - Dec 2022
|  | Design Tabel and Procedure Database | Queue
|  | Develop fitur | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Live | Queue
21 | Develop module tarif shippingline DoSS | Design Flow Concept | On Progress | Approve | AR | AR | 2021-12-27 |  | Jan 2022 - Dec 2022
|  | Design Tabel and Procedure Database | Queue
|  | Develop fitur | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Live | Queue
22 | Re-Design Website Project | Kick off project with vendor | Queue | - | MH |  |  |  | Jan 2022 - Dec 2022
|  | Develop project with vendor | Queue
|  | Develop API Interation | Queue
|  | System integration test | Queue
|  | UAT | Queue
|  | Training | Queue
|  | Go-Live | Queue
23 | Develop fitur void invoice terminal | Design Tabel and Procedure Database | Queue | - | AR |  |  |  | Jan 2022 - Dec 2022
|  | Develop fitur | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Live | Queue
24 | Develop sales monitoring domestik | Design concept | Queue | - | AR |  |  |  | Jan 2022 - Dec 2022
|  | Design Tabel and Procedure Database | Queue
|  | Develop fitur | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Live | Queue
25 | Develop modul controlling data reefer container | Design concept | Queue | - | AR |  |  |  | Jan 2022 - Dec 2022
|  | Design Tabel and Procedure Database | Queue
|  | Develop fitur | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Live | Queue
26 | Develop Rounduse application | Design flow concept | Queue | - | MH |  |  |  | Jan 2022 - Dec 2022
|  | Design Tabel and Procedure Database | Queue
|  | Develop fitur | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Live | Queue
27 | Develop ERP | Design flow concept with vendor | Queue | - | MH |  |  |  | Jan 2022 - Dec 2022
|  | Develop and implamentation ERP with vendor | Queue
|  | Testing Application | Queue
|  | Bug Fix | Queue
|  | Training | Queue
|  | Go-Live | Queue